## Weekly Report
Project team |  | C99.Robusta
I. Trained Items
1. General
- Git Flow (main / develop / feature branches, --no-ff merges) - Way of working: OJT sprint schedule, phase-by-phase delivery - Documentation habit (notes per topic, phase output records)
2. Tech stack
- Learn .NET / React
+ Basic knowledge: C#, .NET 10, layered architecture + Web API + Database: EF Core + PostgreSQL + Messaging / event-driven: SNS + SQS (local via Moto), toggle to real AWS + Supporting tools: Redis (cache), Hangfire (background jobs) + Real-time: SignalR (WebSocket push, Redis backplane) + Auth: JWT-based role authorization (Admin / Employee) + CI/CD: GitHub Actions (build + test on push) + Testing: xUnit, WireMock + Observability: Splunk + Frontend: React (Vite + TypeScript + Tailwind), shadcn/ui component library + Reverse proxy: nginx
- Sample/Demo/Mockup project: Booking System (room / facility booking)
II. Weekly Report
# | Tasklist | Start Date (MM/DD/YYYY) | End Date (MM/DD/YYYY) | Estimated Time (Hour) | Expected Output/ Acceptance Criteria | Status (Open, In-Progress, Done) | Actual Output | Reference Docs Link | Notes
1 | Implement My Preferences (Feature #4) | 09/12/2026 | 09/13/2026 |  | Backend endpoints and Shadcn Switch UI | Done | Built preference endpoints and UI toggles | ui/Booking.UI/src/pages/MyPreferencesPage.tsx
2 | Implement Team Directory (Feature #5) | 09/13/2026 | 09/14/2026 |  | Live availability calculation and HTML table | Done | Added department field and dynamic availability logic | src/Booking.Application/Services/UserService.cs
3 | Migrate System Settings to Database | 09/14/2026 | 09/15/2026 |  | Remove appsettings hardcodes | Done | Created SystemSettings table and refactored RuleEngine | src/Booking.Domain/Entities/SystemSettings.cs
4 | Kanban Maintenance Board | 09/16/2026 | 09/17/2026 |  | Drag and drop maintenance tracking | Done | HTML5 Drag/Drop implemented with backend integration | ui/Booking.UI/src/pages/AdminMaintenancePage.tsx
5 | UI Standardization & Polish | 09/17/2026 | 09/18/2026 |  | Consistent headers and audit log viewers | Done | Standardized page headers, added audit log JSON modal viewer | ui/Booking.UI/src/pages/AdminAuditLogsPage.tsx
6 | Fix Check-in and Auto-Cancel Logic | 09/18/2026 | 09/18/2026 |  | Resolve disappearing buttons and erroneous cancellations | Done | Fixed logic bugs in UI and SQS worker | src/Booking.Application/Services/ReservationService.cs
7 | Phase 3 Technical Documentation | 09/18/2026 | 09/18/2026 |  | Update PagerDuty, Spec-Kit, and Root README | Done | Added system context docs in doc/notes/ | doc/notes/README.md