## Weekly Report
Project team |  | C99.Robusta
I. Trained Items
1. General
- Git Flow (main / develop / feature branches, --no-ff merges) - Way of working: OJT sprint schedule, phase-by-phase delivery - Documentation habit (notes per topic, phase output records)
2. Tech stack
- Learn .NET / React
+ Basic knowledge: C#, .NET 10, layered architecture + Web API + Database: EF Core + PostgreSQL + Messaging / event-driven: SNS + SQS (local via Moto), toggle to real AWS + Supporting tools: Redis (cache), Hangfire (background jobs) + Real-time: SignalR (WebSocket push, Redis backplane) + Auth: JWT-based role authorization (Admin / Employee) + CI/CD: GitHub Actions (build + test on push) + Testing: xUnit, WireMock + Observability: Splunk + Frontend: React (Vite + TypeScript + Tailwind), shadcn/ui component library + Reverse proxy: nginx
- Sample/Demo/Mockup project: Booking System (room / facility booking)
II. Weekly Report
# | Tasklist | Start Date (MM/DD/YYYY) | End Date (MM/DD/YYYY) | Estimated Time (Hour) | Expected Output/ Acceptance Criteria | Status (Open, In-Progress, Done) | Actual Output | Reference Docs Link | Notes
1 | Bug Fix: UI compilation errors in ManageUsersPage | 09/21/2026 | 09/21/2026 |  | Fix compilation errors and broken UI | Done | Fixed UI compilation errors in ManageUsersPage, implemented cache invalidation for room webhooks and amenities | ui/Booking.UI/src/pages/ManageUsersPage.tsx
2 | Refactor: UI consistency, pagination, kanban board styling, and global theme | 09/21/2026 | 09/21/2026 |  | Consistent UI styling across all pages | Done | Refactored 11 files: AdminAuditLogsPage pagination, AdminMaintenancePage kanban, ColleagueDirectoryPage, LoginPage, ManageUsersPage, and global theme tweaks | ui/Booking.UI/src/pages/ | Major UI polish pass
3 | Frontend: Rebranding to BookSpace with geometric logo and local avatars | 09/24/2026 | 09/24/2026 |  | New brand identity with logo, favicon, and avatar system | Done | Integrated geometric logo, updated favicon, added local avatar images, rebranded across 28 files, created phase-3.md output doc | ui/Booking.UI/public/logo.svg
4 | Frontend: Switch to DiceBear API dynamic avatars | 09/24/2026 | 09/24/2026 |  | Dynamic avatar generation per user | Done | Replaced static mock avatars with DiceBear API (notionists style), then randomized styles deterministically based on username | ui/Booking.UI/src/lib/avatar.ts
5 | Frontend: Improve Preferences and Admin Settings save UX | 09/24/2026 | 09/24/2026 |  | Inline save feedback instead of raw alerts | Done | Added inline save feedback with success/error states to MyPreferencesPage and AdminSettingsPage | ui/Booking.UI/src/pages/MyPreferencesPage.tsx
6 | Frontend: UserMenu improvements with quick links and online status | 09/24/2026 | 09/24/2026 |  | Enhanced user menu with navigation and status | Done | Added quick links (My Bookings, Preferences, Insights) and online status indicator to UserMenu dropdown | ui/Booking.UI/src/components/UserMenu.tsx
7 | Frontend: Personal Insights page with meeting analytics | 09/24/2026 | 09/24/2026 |  | New page showing personal booking/meeting analytics | Done | Created MyInsightsPage with charts, wired up to aggregate real reservation data (170+ lines of data logic), added sidebar nav and route | ui/Booking.UI/src/pages/MyInsightsPage.tsx
8 | Frontend: Booking progress bar and live reservation tracking | 09/24/2026 | 09/24/2026 |  | Visual progress indicators for bookings | Done | Added dynamic progress bar to BookingFormModal submit, live ongoing reservation progress bar in MyBookingsPage and BookingDetailModal | ui/Booking.UI/src/components/BookingFormModal.tsx
9 | Style: Favicon high-contrast update | 09/25/2026 | 09/25/2026 |  | Favicon visible on both dark and light backgrounds | Done | Updated favicon with adaptive high-contrast indigo for dark/light themes, added solid white rounded background for guaranteed contrast | ui/Booking.UI/public/favicon.svg
10 | Style: Settings and Preferences sidebar tabs layout | 09/25/2026 | 09/25/2026 |  | Modern two-column / sidebar tabs layout for settings pages | Done | Refactored AdminSettingsPage and MyPreferencesPage to modern two-column layout, then switched to sidebar tabs layout | ui/Booking.UI/src/pages/AdminSettingsPage.tsx