## Weekly Report
Project team |  | C99.Robusta
I. Trained Items
1. General
- Git Flow (main / develop / feature branches, --no-ff merges) - Way of working: OJT sprint schedule, phase-by-phase delivery - Documentation habit (notes per topic, phase output records)
2. Tech stack
- Learn .NET / React
+ Basic knowledge: C#, .NET 10, layered architecture + Web API + Database: EF Core + PostgreSQL + Messaging / event-driven: SNS + SQS (local via Moto), toggle to real AWS + Supporting tools: Redis (cache), Hangfire (background jobs) + Real-time: SignalR (WebSocket push, Redis backplane) + Auth: JWT-based role authorization (Admin / Employee) + CI/CD: GitHub Actions (build + test on push) + Testing: xUnit, WireMock + Observability: Splunk + Frontend: React (Vite + TypeScript + Tailwind), shadcn/ui component library + Reverse proxy: nginx
- Sample/Demo/Mockup project: Booking System (room / facility booking)
II. Weekly Report
# | Tasklist | Start Date (MM/DD/YYYY) | End Date (MM/DD/YYYY) | Estimated Time (Hour) | Expected Output/ Acceptance Criteria | Status (Open, In-Progress, Done) | Actual Output | Reference Docs Link | Notes
1 | Self-learning: Kubernetes (k8s) | 2026-10-12 | 2026-10-16 |  | Understand Kubernetes architecture, workloads, services, and cluster orchestration | Done | Studied Kubernetes architecture, Pods, Deployments, Services (ClusterIP, NodePort, LoadBalancer), Ingress, ConfigMaps, and Secrets |  | Self-learning
2 | Self-learning: Networking | 2026-10-13 | 2026-10-13 |  | Understand computer networking fundamentals, OSI & TCP/IP models, and network protocols | Done | Studied OSI 7-layer model, TCP/IP stack, IP addressing (IPv4/IPv6, CIDR, subnets), DNS resolution, routing, and HTTP/HTTPS protocols |  | Self-learning
3 | Self-learning: SSH | 2026-10-14 | 2026-10-14 |  | Understand SSH protocol, authentication methods, configuration, and secure remote server management | Done | Studied SSH key pair authentication (ed25519, RSA), ssh-agent, ~/.ssh/config host configuration, remote access, and port forwarding / tunneling |  | Self-learning
4 | Self-learning: UFW | 2026-10-15 | 2026-10-15 |  | Understand Linux host security and firewall configuration using UFW (Uncomplicated Firewall) | Done | Studied UFW default policies (deny incoming, allow outgoing), rule configuration (allowing SSH, HTTP, HTTPS, custom ports), service rules, and firewall status management |  | Self-learning
5 | Self-learning: Design Patterns | 2026-10-16 | 2026-10-16 |  | Understand common software design patterns and their practical applications in software development | Done | Studied Creational patterns (Singleton, Factory Method, Builder), Structural patterns (Adapter, Decorator, Facade), and Behavioral patterns (Observer, Strategy, Repository) |  | Self-learning
6 | Training: Complete "ISMS Refresh Training S2 2026 for All (GR 1-4) by ISM" course | 2026-10-16 | 2026-10-16 |  | Complete mandatory ISMS information security awareness training and pass assessment | Done | Completed the course "ISMS Refresh Training S2 2026 for All (GR 1-4) by ISM" and passed the assessment |  | Company training