## Weekly Report
Project team |  | C99.Robusta
I. Trained Items
1. General
- Git Flow (main / develop / feature branches, --no-ff merges) - Way of working: OJT sprint schedule, phase-by-phase delivery - Documentation habit (notes per topic, phase output records)
2. Tech stack
- Learn .NET / React
+ Basic knowledge: C#, .NET 10, layered architecture + Web API + Database: EF Core + PostgreSQL + Messaging / event-driven: SNS + SQS (local via Moto), toggle to real AWS + Supporting tools: Redis (cache), Hangfire (background jobs) + Real-time: SignalR (WebSocket push, Redis backplane) + Auth: JWT-based role authorization (Admin / Employee) + CI/CD: GitHub Actions (build + test on push) + Testing: xUnit, WireMock + Observability: Splunk + Frontend: React (Vite + TypeScript + Tailwind), shadcn/ui component library + Reverse proxy: nginx
- Sample/Demo/Mockup project: Booking System (room / facility booking)
II. Weekly Report
# | Tasklist | Start Date (MM/DD/YYYY) | End Date (MM/DD/YYYY) | Estimated Time (Hour) | Expected Output/ Acceptance Criteria | Status (Open, In-Progress, Done) | Actual Output | Reference Docs Link | Notes
1 | Add GitHub Actions CI pipeline | 08/29/2026 | 08/29/2026 |  | CI runs build and tests automatically on every push | Done | Workflow added: restore -> build -> unit tests -> integration tests | .github/workflows/ci.yml
2 | Add SignalR real-time hub for reservations and notifications | 08/30/2026 | 08/30/2026 |  | Server can push live updates to connected clients without polling | Done | SignalR hub wired into Api and Worker with a Redis backplane | src/Booking.Infrastructure/Hubs
3 | Build the room booking flow in the UI with live updates; make nginx a real reverse proxy | 08/31/2026 | 08/31/2026 |  | Users can browse rooms, see availability change live, and book from the browser | Done | Booking flow wired to the real Api; ui's nginx now proxies /api and /hubs to the Api | ui/Booking.UI; src/docker-compose.yml
4 | Redesign the booking calendar as a day-view timeline with modals | 08/31/2026 | 08/31/2026 |  | Calendar shows a day at a glance; booking and viewing details happen in a modal, not a full page | Done | Horizontal-timeline calendar (indigo theme), booking-form and detail modals | ui/Booking.UI/src/components/RoomCalendar.tsx
5 | Add role-based authorization for room creation, plus sidebar nav, month view, and stats panel | 08/31/2026 | 08/31/2026 |  | Only Admins can create rooms; the UI reflects the signed-in user's role and offers a month view | Done | Admin vs Employee enforced end-to-end (Api + UI); sidebar nav, month view, stats panel added | src/Booking.Api/Controllers/RoomsController.cs; ui/Booking.UI/src/components/Sidebar.tsx
6 | Add Docker Compose profiles for faster dev iteration | 09/01/2026 | 09/01/2026 |  | Can start only the services a given task needs instead of the whole stack every time | Done | mock-aws / logging / backend / frontend profiles added and documented | src/docker-compose.yml; README.md
7 | Show who booked each room; fix a real user-data leak found along the way | 09/03/2026 | 09/03/2026 |  | Calendar shows the booking owner's name, not just that a slot is taken | Done | Reservation responses now carry the booker's username; fixed GET /api/users leaking password hashes with no auth check | src/Booking.Application/Services/ReservationService.cs; src/Booking.Api/Controllers/UsersController.cs
8 | Add drag-to-quick-fill for multi-hour bookings | 09/03/2026 | 09/03/2026 |  | User can drag across hours on the calendar to select a multi-hour range in one motion | Done | Drag interaction added, clamped so a drag can't cross an existing booking | ui/Booking.UI/src/components/RoomCalendar.tsx
9 | Fix Splunk's and Redis's Docker volumes leaking on every container restart | 09/03/2026 | 09/03/2026 |  | Recreating a container doesn't accumulate orphaned anonymous volumes | Done | Named volumes added for both images' internally-declared VOLUME paths | src/docker-compose.yml
10 | Cache the full reservation list in Redis - the actual hot read path | 09/03/2026 | 09/03/2026 |  | The list every client re-fetches on page load and on every live update stops hammering Postgres | Done | GetAllAsync cached under one key, invalidated on create/cancel; live-verified against real Redis | src/Booking.Infrastructure/Persistence/Repositories/CachedReservationRepository.cs
11 | Adopt shadcn/ui as the component foundation, migrate real forms, redesign the UI theme | 09/03/2026 | 09/04/2026 |  | Consistent, modern component library and visual design (incl. light/dark) across the app | Done | shadcn/ui foundation added; login/create-room/booking forms migrated; full theme redesign across every page | ui/Booking.UI/src/components/ui
12 | Organize the documentation vault (Obsidian) with real cross-links between notes | 09/04/2026 | 09/04/2026 |  | Related topic notes are actually connected in the Obsidian graph, not isolated dots | Done | Converted prose references to real [[wikilinks]]; added a Related Notes section to every note | doc/notes | Documentation only
13 | Fix reservation create/cancel silently blocking on a slow external call | 09/04/2026 | 09/04/2026 |  | Booking/canceling responds quickly regardless of how slow the downstream event publish is | Done | Publish moved off the request's critical path; response time dropped from up to ~20s to well under 1s | src/Booking.Application/Services/ReservationService.cs
14 | Reject reservations that start in the past | 09/04/2026 | 09/04/2026 |  | A room can no longer be booked for a date/time that has already passed | Done | Backend rule added (with tests), plus a matching date-picker restriction in the UI | src/Booking.Application/Services/BookingRuleEngine.cs
15 | Add backend support for deactivating a room (maintenance mode) | 09/04/2026 | 09/04/2026 |  | An inactive room can't be newly booked but keeps its full booking history | Done | Deactivate/reactivate endpoints added, admin-only; the booking list now excludes inactive rooms | src/Booking.Api/Controllers/RoomsController.cs | Backend only - UI to follow