## Weekly Report
Project team |  | C99.Robusta
I. Trained Items
1. General
- Git Flow (main / develop / feature branches, --no-ff merges) - Way of working: OJT sprint schedule, phase-by-phase delivery - Documentation habit (notes per topic, phase output records)
2. Tech stack
- Learn .NET / React
+ Basic knowledge: C#, .NET 10, layered architecture + Web API + Database: EF Core + PostgreSQL + Messaging / event-driven: SNS + SQS (local via Moto), toggle to real AWS + Supporting tools: Redis (cache), Hangfire (background jobs) + Real-time: SignalR (WebSocket push, Redis backplane) + Auth: JWT-based role authorization (Admin / Employee) + CI/CD: GitHub Actions (build + test on push) + Testing: xUnit, WireMock + Observability: Splunk + Frontend: React (Vite + TypeScript + Tailwind), shadcn/ui component library + Reverse proxy: nginx
- Sample/Demo/Mockup project: Booking System (room / facility booking)
II. Weekly Report
# | Tasklist | Start Date (MM/DD/YYYY) | End Date (MM/DD/YYYY) | Estimated Time (Hour) | Expected Output/ Acceptance Criteria | Status (Open, In-Progress, Done) | Actual Output | Reference Docs Link | Notes
1 | Integrate Microsoft Semantic Kernel and build AI Booking Concierge UI | 09/05/2026 | 09/07/2026 |  | Working interactive chat interface answering booking queries | Done | Built backend plugins and React chat interface with interactive attendee selection | src/Booking.Application/Services/ChatService.cs
2 | Add maintenance overlay and prevent cancellation of started bookings | 09/08/2026 | 09/08/2026 |  | Deactivated rooms block new bookings; active reservations cannot be cancelled | Done | Maintenance overlay implemented on calendar; business rules updated in API | ui/Booking.UI/src/components/RoomCalendar.tsx
3 | Decouple frontend from API and add CI frontend verification | 09/08/2026 | 09/09/2026 |  | CI pipeline checks frontend builds; Nginx decoupled | Done | Frontend verification and dependency caching added to GitHub Actions | .github/workflows/ci.yml
4 | Configure dynamic CORS and telemetry (New Relic APM) | 09/09/2026 | 09/10/2026 |  | API accepts cross-origin requests; APM agent installed | Done | API CORS configured via env vars; New Relic agent in Dockerfiles | src/Booking.Api/Program.cs
5 | Deploy to Render (Web Service) and Supabase (PostgreSQL) | 09/10/2026 | 09/11/2026 |  | Live production deployment with combined API/Worker container | Done | Unified Dockerfile and entrypoint script; concurrent EF migrations fixed | src/Dockerfile.render
6 | Remove seeded admin login and fix production UI bugs | 09/11/2026 | 09/11/2026 |  | Production-ready UI deployed via Netlify | Done | Removed dev-only UI buttons and unused imports fixing TS build errors | ui/Booking.UI/src/pages/LoginPage.tsx