## Weekly Report
Project team |  | C99.Robusta
I. Trained Items
1. General
- Git Flow (main / develop / feature branches, --no-ff merges) - Way of working: OJT sprint schedule, phase-by-phase delivery - Documentation habit (notes per topic, phase output records)
2. Tech stack
- Learn .NET / React
+ Basic knowledge: C#, .NET 10, layered architecture + Web API + Database: EF Core + PostgreSQL + Messaging / event-driven: SNS + SQS (local via Moto), toggle to real AWS + Supporting tools: Redis (cache), Hangfire (background jobs) + Real-time: SignalR (WebSocket push, Redis backplane) + Auth: JWT-based role authorization (Admin / Employee) + CI/CD: GitHub Actions (build + test on push) + Testing: xUnit, WireMock + Observability: Splunk + Frontend: React (Vite + TypeScript + Tailwind), shadcn/ui component library + Reverse proxy: nginx
- Sample/Demo/Mockup project: Booking System (room / facility booking)
II. Weekly Report
# | Tasklist | Start Date (MM/DD/YYYY) | End Date (MM/DD/YYYY) | Estimated Time (Hour) | Expected Output/ Acceptance Criteria | Status (Open, In-Progress, Done) | Actual Output | Reference Docs Link | Notes
1 | Backend: Add check-in window to SystemSettings | 09/28/2026 | 09/28/2026 |  | Configurable check-in window via admin settings | Done | Created DB migration (AddCheckinWindowMinutes), API endpoint, updated ReservationService logic, expanded AdminSettingsPage UI | src/Booking.Domain/Entities/SystemSettings.cs
2 | Backend: Add Redis caching behavior to MediatR pipeline | 09/28/2026 | 09/28/2026 |  | Distributed caching via MediatR pipeline behaviors | Done | Wired Redis distributed cache into CachingBehavior and CacheInvalidationBehavior | src/Booking.Application/Features/Common/Caching/CachingBehavior.cs
3 | Frontend: Add agenda view, mini calendar, and update stats panel | 09/28/2026 | 09/28/2026 |  | Enhanced HomePage with agenda and calendar widgets | Done | Created AgendaView (142 lines), MiniCalendar (152 lines), refactored HomePage (640+ insertions), updated StatsPanel and BookingFormModal | ui/Booking.UI/src/components/AgendaView.tsx
4 | Bug Fix: Redis configuration mapping and TypeScript strictness errors | 09/28/2026 | 09/28/2026 |  | Fix build and runtime errors | Done | Corrected Redis config mapping in Program.cs, resolved TS strict errors in HomePage and MyInsightsPage | src/Booking.Api/Program.cs
5 | Testing: K6 load tests, Playwright E2E tests, and Integration tests | 09/28/2026 | 09/28/2026 |  | Comprehensive test coverage (load, E2E, integration) | Done | Implemented K6 load test scenarios (browse-rooms), Playwright E2E specs (admin-room, data-fetching split into rooms/users), xUnit integration tests (HealthCheck, Reservation). 440+ new lines | src/test/Booking.LoadTests/main.js
6 | Documentation: Update phase 3 notes (EC2, GitHub Actions, MediatR) | 09/28/2026 | 09/28/2026 |  | Updated research documentation | Done | Updated aws-ec2.md, expanded github-actions.md (84 lines rewritten), added MediatR caching notes | doc/notes/phase-3/github-actions.md | Research notes
7 | Backend: Prevent double-booking (same user, overlapping time) | 09/29/2026 | 09/29/2026 |  | Validation rule blocking concurrent room bookings per user | Done | Added overlap check in BookingRuleEngine, updated IBookingRuleEngine interface, ReservationRepository, and ReservationService. Created HLD.md doc | src/Booking.Application/Services/BookingRuleEngine.cs
8 | Bug Fix: UI fixes (calendar overflow, check-in error modals, Recharts colors) | 09/29/2026 | 09/29/2026 |  | Resolve visual bugs across multiple pages | Done | Fixed RoomCalendar width overflow (3 commits), added error banners to BookingDetailModal and MyBookingsPage check-in/cancel, removed hardcoded hsl() for Tailwind v4 oklch | ui/Booking.UI/src/components/RoomCalendar.tsx
9 | Bug Fix: Integration test fixes (parallel execution, Moq compilation) | 09/29/2026 | 09/29/2026 |  | Integration tests pass reliably | Done | Disabled parallel execution to prevent EF Core migration races, fixed Moq setup errors caused by rule engine signature change | src/test/Booking.IntegrationTests/ReservationIntegrationTests.cs
10 | Documentation: Finalize phase 3 output, update project plan to 100% | 09/29/2026 | 09/29/2026 |  | Phase 3 completion documentation | Done | Finalized phase-3.md output document, updated plan.md to 100% complete, updated README | doc/phase-outputs/phase-3.md
11 | Final project demo presentation | 09/29/2026 | 09/29/2026 |  | Present BookSpace project demo | Done | Demonstrated BookSpace booking system features and architecture
12 | Self-learning: Rally study | 10/01/2026 | 10/01/2026 |  | Understand Rally project management tool | Done | Studied Rally tool for agile project tracking and sprint management |  | Self-learning
13 | Self-learning: Slack study | 10/02/2026 | 10/02/2026 |  | Understand Slack workspace and integrations | Done | Studied Slack communication platform, channels, integrations and workflows |  | Self-learning
14 | Self-learning: Continuous learning throughout the week | 09/28/2026 | 10/02/2026 |  | Ongoing skill development | In-Progress | Studied Redis caching patterns, K6 load testing, Playwright E2E, MediatR pipeline behaviors |  | Self-learning