## Weekly Report
Project team |  | C99.Robusta
I. Trained Items
1. General
- Git Flow (main / develop / feature branches, --no-ff merges) - Way of working: OJT sprint schedule, phase-by-phase delivery - Documentation habit (notes per topic, phase output records)
2. Tech stack
- Learn .NET / React
+ Basic knowledge: C#, .NET 10, layered architecture + Web API + Database: EF Core + PostgreSQL + Messaging / event-driven: SNS + SQS (local via Moto), toggle to real AWS + Supporting tools: Redis (cache), Hangfire (background jobs) + Testing: xUnit, WireMock + Observability: Splunk + Frontend: React (Vite + TypeScript + Tailwind)
- Sample/Demo/Mockup project: Booking System (room / facility booking)
II. Weekly Report
# | Tasklist | Start Date (MM/DD/YYYY) | End Date (MM/DD/YYYY) | Estimated Time (Hour) | Expected Output/ Acceptance Criteria | Status (Open, In-Progress, Done) | Actual Output | Reference Docs Link | Notes
1 | Write up Phase 2 results and update the project plan | 2026-08-24 | 2026-08-24 |  | Phase 2 work recorded task-by-task; plan status current | Done | Phase 2 output doc written; plan shows Phases 1-2 complete, ahead of the Aug 31 target | doc/phase-outputs/phase-2.md; doc/plan.md
2 | Fix time zone handling for bookings and reminders | 08/24/2026 | 08/24/2026 |  | Opening hours and reminder messages show the correct local time, not a global one | Done | Local-time handling in place with settings and tests covering it | src/Booking.Application
3 | Study notes - background jobs (Hangfire) | 08/24/2026 | 08/24/2026 |  | Short note on what it does and how it fits this project | Done | Note completed | doc/notes/hangfire.md | Research only
4 | Study notes - caching (Redis) | 08/25/2026 | 08/25/2026 |  | Short note on what it does and how it fits this project | Done | Note completed | doc/notes/redis.md | Research only
5 | Make error messages in the web app readable | 08/25/2026 | 08/25/2026 |  | When something fails, the user sees a clear message instead of raw technical text | Done | App now shows readable error messages | ui/Booking.UI
6 | Study notes - logging/monitoring (Splunk) | 08/26/2026 | 08/26/2026 |  | Short note on what it does and how it fits this project | Done | Note completed | doc/notes/splunk.md | Research only
7 | Study notes - API mocking for tests (WireMock) | 08/26/2026 | 08/26/2026 |  | Short note on what it does and how it fits this project | Done | Note completed | doc/notes/wiremock.md | Research only
8 | Allow switching between the local test setup and real cloud services | 08/27/2026 | 08/27/2026 |  | Messaging can move between local practice mode and real cloud via a settings change, no code edits | Done | Config-only toggle working; example settings file added | src/.env.example; doc/notes/moto.md
9 | Improve reminder emails | 08/28/2026 | 08/28/2026 |  | Reminder emails go out clean and formatted, with booking details highlighted | Done | Styled HTML reminder emails with a details card | src/Booking.Infrastructure